## Product backlog
ID | Feature | User / Technical Story | Acceptance Criteria | Story Points | Jira Key
Sprint 1 (22 Sep to 20 Oct): Data, model and app |  |  |  | 83
US_01 | Data Pipeline | As the development team, we need clean per-eye labels, a patient-level split and preprocessed photos, so the model can be trained and tested fairly. | Per-eye labels taken from each eye's own keywords pass the verification script; patients are split 70/15/15 with seed 42; one shared preprocessing function runs on every photo; code is merged into main. | 23 | SCRUM-142
US_02 | Dual-Head Model | As a screening technician, I want one photo to give both a cataract and a glaucoma result, so I can triage both conditions in one step. | A shared ResNet with two heads trains end to end on the real labels, weights rare cases, never reads external data, and passes the smoke test. | 16 | SCRUM-143
US_03 | External Test Sets | As a reviewer, I want the model tested on outside datasets it never trained on, so I can trust that it works beyond ODIR-5K. | Test-only labels for ORIGA, DRISHTI-GS, ACRIMA and retina_dataset_2016 have checked counts; the overlap check passes; the metrics protocol is written; calibration code is ready and uses the validation split only. | 15 | SCRUM-144
US_04 | App Prototype (carried over to Sprint 2) | As a screening technician, I want to upload a patient's fundus photo and see a clear cataract and glaucoma result, so I can decide quickly whether the patient should see an eye specialist. | Upload, Results and History screens work; upload shows a preview and rejects non-images; results show separate cataract and glaucoma results from the API, with "Uncertain, refer" as a normal result; mock data only; follows the DUAL branding. | 18 | SCRUM-31
US_05 | Photo Quality Check | As a screening technician, I want the app to stop photos that can't be screened and tell me why, so I don't get a result from an unusable file. | Unreadable, almost-black and non-fundus uploads are blocked with a clear message; hazy or blurry eye photos still go to the model; all ODIR training photos pass; 17 automated tests pass. | 3 | SCRUM-127
US_06 | Model Ablation | As the development team, we want cataract-only, glaucoma-only and shared two-head models trained with identical settings, so we can test whether sharing the backbone helps. | Nine models are saved (3 model types x 3 seeds); the training split is used to learn and the validation split to stop; settings for every run are recorded; no external data is used. | 8 | SCRUM-55
Sprint 2 (planned) |  |  |  | 28
US_07 | Calibration & Abstention | As an optometrist, I want the tool to say "low image quality or uncertain, refer" when it is not sure, so that I do not act on a weak result. | Calibration, one decision threshold per disease and one abstention cutoff are fitted on the validation split only; the frozen values are committed and not changed afterwards. | 5 | SCRUM-56
US_08 | Internal Test | As the development team, we want a within-dataset baseline, so that external results can be compared against it. | All three model types are scored once on the internal test split after calibration is frozen; AUC with 95% confidence interval for each disease; results table is in the repository. | 3 | SCRUM-57
US_09 | External Testing | As a primary care physician, I want to know how the model performs on photos from other clinics, so that I can judge how far to trust its referrals. | ORIGA and DRISHTI-GS are scored with the frozen thresholds and calibration; ACRIMA and retina_dataset_2016 are reported in their own rows; AUC with confidence intervals and calibration for each set. | 5 | SCRUM-58
US_10 | Technical Paper Draft | As a reader of the paper, I want the datasets and limitations described with exact counts, so that I can judge the results. | Dataset and limitations sections use counts from the verification script; the cataract external-testing gap is stated as a limitation; PDF and Word versions are on the wiki. | 5 | SCRUM-59
US_11 | Cataract Haze Check | As a primary care physician, I want to know the cataract result reflects the lens and not a blurry photo, so that I can trust a cataract referral. | The outcome that means "the model detects haze" is written down before results are seen; cataract share is reported for media-opacity and normal eyes; blur curve is plotted against real cataract eyes. | 5 | SCRUM-61
US_16 | Testing and Review | As the team, we want every Sprint 2 story tested and reviewed against its acceptance criteria by someone who did not build it, so that we know each story really works before we close it. | Test cases are written for each Sprint 2 story; each is run and recorded as pass or fail with the date; every pull request for a Sprint 2 story is reviewed before it is merged; problems found are logged in Jira and linked to the story. | 5 | SCRUM-154
Sprint 3 (planned) |  |  |  | 29
US_12 | Glaucoma Heatmap Check | As a primary care physician, I want to see that a glaucoma result is based on the optic disc, so that I can trust the referral. | Grad-CAM heatmaps are produced for ORIGA and DRISHTI-GS; the share of images whose heatmap peak falls inside the disc outline is reported per dataset. | 5 | SCRUM-62
US_13 | Ablation Comparison | As a reader of the paper, I want to know whether sharing one backbone helps, hurts or makes no difference, so that the design choice is justified. | Single-disease and shared models are compared per disease on the internal test and, for glaucoma, on the external tests; spread across seeds is shown; table and conclusion are in the repository. | 3 | SCRUM-63
US_14 | Real Model in App | As an optometrist, I want to upload a fundus photo and get real cataract and glaucoma risk scores, so that I can decide whether to refer. | The app runs on the trained model; "Uncertain, refer" is shown as a normal result; every results table names the commit that produced it; the results commit is tagged before the final demo. | 8 | SCRUM-64
US_15 | Final Documentation | As a developer joining later, I want install, deployment and API manuals, so that I can run and extend the app. | Data card, user manual, deployment manual and API documentation in PDF and Word; final technical paper with its history page; reviewed by the data pipeline and external validation roles. | 8 | SCRUM-65
US_17 | Testing and Review | As the team, we want every Sprint 3 story tested and reviewed against its acceptance criteria by someone who did not build it, so that the final product we demo and hand over really works. | Test cases are written for each Sprint 3 story; each is run and recorded as pass or fail with the date; the full app is tested end to end with the real model before the final demo; every pull request is reviewed before it is merged; problems found are logged in Jira. | 5 | SCRUM-156
|  |  | Total | 140